## Test Cases
TC ID | Bug ID | Module | Test Case Title | Test Steps | Expected Result | Priority | Status | Actual Result | Remarks
TC-001 | BUG-001 | Frontend | Verify the app icon is displayed correctly | 1. Install the app on a device. 2. Check the home screen/app drawer for the app icon. | App icon is displayed correctly on the device. | Low | Failed | App icon is missing. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-002 | BUG-002 | Frontend | Verify the gradient is displayed on the intended screen(s) | 1. Navigate to the screen(s) that should display a gradient background. 2. Check whether the gradient is rendered. | Gradient is displayed correctly as per the design. | Low | Failed | Gradient is missing. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-003 | BUG-003 | Frontend | Verify doodles are displayed on the intended screen(s) | 1. Navigate to the screen(s) that should display doodle graphics. 2. Check whether the doodles are rendered. | Doodles are displayed correctly as per the design. | Low | Failed | Doodles are missing. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-004 | BUG-004 | Frontend | Verify the Username field does not allow spaces | 1. Navigate to the Username field (signup/login). 2. Attempt to enter a username containing spaces. 3. Check whether spaces are accepted. | Username field blocks or strips spaces, not allowing them as part of the username. | Medium | Failed | Username field allows spaces. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-005 | BUG-005 | Backend | Verify the state updates correctly after closing the modal | 1. Trigger an action that opens a modal and changes state. 2. Close the modal. 3. Check whether the underlying screen reflects the updated state. | State is correctly updated and reflected after the modal is closed. | Medium | Failed | State is not updated after closing the modal. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-006 | BUG-006 | Frontend | Verify the Username field enforces a maximum character limit | 1. Navigate to the Username field. 2. Enter a very long username exceeding a reasonable limit. 3. Check whether input is capped. | Username field enforces a maximum character limit and prevents excessive input. | Low | Failed | Username field has no maximum character limit. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-007 | BUG-007 | Frontend | Verify the Password field has validation | 1. Navigate to the Password field (signup/login). 2. Enter an invalid password (e.g., too short, missing required characters). 3. Attempt to submit. | Password field validates the input and blocks submission for invalid passwords. | Medium | Failed | Password field has no validation. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-008 | BUG-008 | Frontend | Verify the modal remains open when displaying "Invalid credentials" or "Username already exists" | 1. Trigger the "Invalid credentials" error (wrong login) or "Username already exists" error (signup). 2. Observe whether the modal stays open with the error message. | Modal remains open, displaying the error message so the user can correct their input. | Medium | Failed | Modal closes automatically when "Invalid credentials" or "Username already exists" is displayed. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-009 | BUG-009 | Frontend | Verify the password visibility (eye) icon is present | 1. Navigate to a Password field. 2. Check for the presence of a visibility toggle (eye) icon. | Password visibility (eye) icon is present, allowing the user to show/hide the password. | Low | Failed | Password visibility (eye) icon is missing. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-010 | BUG-010 | Backend | Verify the app does not crash when clicking Forgot Password or Feedback | 1. Navigate to the Login screen. 2. Click Forgot Password. 3. Separately, click Feedback and observe app behavior. | App handles both actions without crashing. | High | Failed | App crashes when clicking Forgot Password or Feedback. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-011 | BUG-011 | Backend | Verify the username is displayed correctly | 1. Log in with a valid account. 2. Navigate to a screen displaying the username. 3. Check the displayed value against the actual username. | Username is displayed correctly and accurately. | Medium | Failed | Username is displayed incorrectly. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-012 | BUG-012 | Backend | Verify money is deducted only after the Deal action completes, not immediately on click | 1. Note the current balance. 2. Click Deal. 3. Check when the balance is actually deducted. | Money is deducted at the correct point in the game flow, not immediately upon clicking Deal. | High | Failed | Money is deducted immediately when clicking Deal. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-013 | BUG-013 | Backend | Verify a "Not enough money" message is shown instead of allowing a negative balance | 1. Reduce the balance to 0. 2. Attempt to place a bet/deal that requires more money. 3. Check the system's response. | System displays "Not enough money" and prevents the balance from going negative. | High | Failed | Balance goes into negative after reaching 0 instead of displaying "Not enough money." | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-014 | BUG-014 | Backend | Verify the Logout button is hidden when the user is playing without logging in | 1. Start playing the game without logging in (guest mode). 2. Check for the presence of a Logout button. | Logout button is not displayed for users playing without logging in. | Low | Failed | Logout button is visible even when the user is playing without logging in. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-015 | BUG-015 | Frontend | Verify screen size is consistent throughout the application | 1. Navigate across multiple screens in the app. 2. Check whether the screen size/scaling remains consistent. | Screen size remains consistent across all screens in the application. | Medium | Failed | Screen size is not consistent throughout the application. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-016 | BUG-016 | Frontend | Verify the Android navigation bar is visible | 1. Open the app on an Android device. 2. Check for the presence of the navigation bar. | Android navigation bar remains visible while using the app. | Medium | Failed | Android navigation bar is hidden. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-017 | BUG-017 | Frontend | Verify Pair Plus numbers are displayed on the slider | 1. Navigate to the Pair Plus betting section. 2. Check whether numbers are displayed on the slider. | Pair Plus numbers are displayed correctly on the slider. | Medium | Failed | Pair Plus numbers are not displayed on the slider. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-018 | BUG-018 | Backend | Verify the Pair Plus button is present | 1. Navigate to the game screen. 2. Check for the presence of the Pair Plus button. | Pair Plus button is present and available for use. | Medium | Failed | Pair Plus button is missing. | Bug still marked "Open" in bug report — retest once fix is deployed.

## Summary
Three Card Myrtle - Test Case Summary
Total Bugs Covered | 18
Total Test Cases | 18
Frontend Module Bugs | 11
Backend Module Bugs | 7
High Priority | 3
Medium Priority | 9
Low Priority | 6
Passed | 0
Failed | 18